## ✦ Start Here
THE FILTER
A live demonstration model · Left Brain Consulting
This workbook is a working example of The Filter, pre-loaded with a fictional mid-market company's improvement portfolio — 30 real-world initiatives, each scored, ranked, and tracked exactly the way your team's would be. Everything you see updates automatically from one list.
HOW THE SCORE WORKS
IMPACT | URGENCY | AUDIENCE | Scored 1·3·5·8·13 on each. Weighted into one number that ranks the whole list.
40% of the score | 40% of the score | 20% of the score
How much does this change the business if we do it? | What's the cost of waiting? | Who's asking — and how much pressure is behind it?
WEIGHTED SCORE = (Impact × 0.40) + (Urgency × 0.40) + (Audience × 0.20)
WHERE TO LOOK
📊 Exec Dashboard | The one-screen view leadership lives in — every initiative grouped by status, the off-track and at-risk work surfaced first, flagged items up top.
📋 Raw Data – The Filter | The single list. Every initiative with its scores, owner, status, ROI estimate, and the reasoning behind each score. This is the source of truth everything else reads from.
📊 Scoring Guide | The shared definitions. What a 13 means versus a 5 — so every person scores against the same language, not their own gut.
📐 ROI Calculator | The cost-of-chaos math — what stalled and duplicated work is quietly costing, and what gets reclaimed.
The list is simple on purpose. The discipline is what's hard — and that's the part I install. Decide what matters, make it visible, and watch the right work get finished.
Nathan Harris · nathan@leftbrainconsult.com · leftbrainconsult.com

## 📊 Scoring Guide
THE FILTER — SCORING GUIDE
Use this to justify your score. The 'Why' field in your submission should reference language from this table.
IMPACT (40%) | How much does this change the business if we do it? |  | URGENCY (40%) | What's the cost of waiting? |  | AUDIENCE (20%) | Who is asking for this — and how much pressure is behind it?
Score | Label | What it means — use this in your Why field | Score | Label | What it means — use this in your Why field | Score | Label | What it means — use this in your Why field
13 | Game Changer | Transforms the business. Shifts competitive position, revenue model, or customer retention curve. The kind of result that defines the year. | 13 | Time Bomb | Delay has direct financial, legal, or customer consequences. A hard deadline, a compliance date, a churn risk already in motion. Every week costs something real. | 13 | External + Internal Pressure | Customers are asking. Leadership is asking. The team sees it. Multi-directional demand. Hard to ignore without a real reason.
8 | Major Lift | Meaningfully moves a key metric across the whole company. Measurable, significant, lasting. Multiple teams notice. | 8 | Window Closing | Competitive or market pressure building. Not a crisis yet, but the window to act is narrowing. Inaction has a cost that compounds. | 8 | Customer-Driven | Direct request or clear signal from customers or the market. Not internal opinion — external pull with real stakes attached.
5 | Solid Improvement | Real value, real progress. Makes something meaningfully better for a function or customer segment. Worth the investment. | 5 | Growing Pain | Gets worse the longer we wait, but not catastrophically. Should be in this quarter's plan. No hard deadline but clear trajectory. | 5 | Leadership Priority | A sponsor at the executive level is behind this. Organizational weight, but limited external signal. Top-down, not bottom-up.
3 | Incremental | Helpful but narrow. Fixes something specific. Limited blast radius. Business operates fine either way. | 3 | Backburner | Stable problem. Can wait a quarter without meaningful consequence. Worth doing but no urgency driving it. | 3 | Team Request | Internal ask from the people doing the work. Real signal, valuable perspective, but limited external pull.
1 | Nice to Have | Polish. Good if it happens, invisible if it doesn't. No meaningful impact on outcomes. | 1 | Whenever | No time pressure at all. Truly optional timing. Will matter eventually, not today. | 1 | Individual Idea | One person's suggestion. May be brilliant. The demand is self-generated — no external or organizational validation yet.
WEIGHTING: Impact = 40% ¦ Urgency = 40% ¦ Audience = 20% ¦ Formula: (Impact × 0.4) + (Urgency × 0.4) + (Audience × 0.2) ¦ Scale: 1, 3, 5, 8, 13
SCALE: 13 = highest · 1 = lowest · Select from dropdown — the label is part of the value
The score ranks the list. The review session starts at the highest score and works down. Multiple high scores = a tradeoff conversation, not an automatic activation. Humans decide.

## 📋 Raw Data - The Filter
ID | Submission Date | Submitter | Department Impacted | Title | Description | Type | Strategic Alignment | Sponsor | Impact (1,3,5,8,13) | Why this Impact score? | Urgency (1,3,5,8,13) | Why this Urgency score? | Audience (1,3,5,8,13) | Who is asking & why this score? | Weighted Score | Risk of NOT Doing This | Current State Time Cost | Definition of Done | ROM ROI Value ($) | Effort (S/M/L/XL) | Project Status | % Complete | Latest Project Update | Delivery Lead | Target Completion Month | Executive Notes | Escalated | Fast Track | Primary Value Driver | % Allocated (Lead’s time) | _ActiveLoadWeight | _IsActive
F-000 | 2025-01-06 | Sarah Chen | Operations | Automate weekly status report generation | Every Friday ops team manually compiles updates from 6 sources into a slide deck. Takes 3 hours across 2 people. | AI Initiative | Operational Efficiency | COO | 8 - Major Lift | Clear, high-frequency task. Fully automatable with existing tools. Immediate time recapture. | 8 - Window Closing | Happens every week. No hard deadline but cost compounds — 150+ hours wasted annually. | 5 - Leadership Priority | Primarily serves COO and department heads. Cross-functional visibility but limited external impact. | 7.4 | If we don't automate this, we continue spending 150+ hrs/yr on a report nobody reads fully. Reporting quality stays inconsistent. | 3 hours every Friday across 2 people (Sarah Chen + ops analyst) | Report generated in under 30 minutes with no manual data pulling. Consistent format every week. | 15000 | M — Medium | 🔵 06 - Delivered | 100% |  | Nathan Harris | Jan |  | FALSE | FALSE | 🟢 Revenue Growth | 10% | 0 | 0
F-001 | 2025-01-08 | Priya Nair | Finance | Build rolling 13-week cash flow model | Finance has no forward visibility on cash position. CFO is manually updating a static spreadsheet weekly with no scenario modeling. | Process Improvement | Financial Visibility | CFO | 13 - Game Changer | No cash visibility is a material risk. One bad month without warning could force emergency decisions. | 8 - Window Closing | We're entering a growth phase. Need this before Q2 hiring decisions or we're flying blind. | 8 - Customer-Driven | Serves CFO directly. Board and CEO rely on this for every capital decision. | 10 | We make hiring and investment decisions without knowing our cash runway. One unexpected cost event could create a crisis. | 4 hours/week CFO manually updating static model. Zero scenario modeling capability. | Rolling 13-week model live. CFO updates in under 30 min. 3 scenarios (base, upside, stress) available at all times. | 40000 | L — Large | ⚪ 01 - Not Started | 0% |  | TBD | Sep |  | FALSE | FALSE | 🟡 Hard Cost Savings | 15% | 0 | 0
F-002 | 2025-01-07 | Marcus Webb | Sales | CRM data cleanup and deduplication | Salesforce has 40% duplicate contact records from 3 years of manual entry. Causing missed follow-ups and inaccurate forecasting. | Tech Request | Revenue Growth | VP Sales | 5 - Solid Improvement | Fixes a real problem but doesn't grow revenue directly — it stops revenue leakage from poor data. | 13 - Time Bomb | Forecasting for Q1 board review is in 3 weeks. Bad data makes us look unprepared to the board. | 8 - Customer-Driven | VP Sales owns this. Impacts the entire sales team's daily workflow and board-level reporting. | 8.8 | Q1 board forecast will be inaccurate. Sales reps will continue working duplicate leads. Pipeline visibility stays broken. | ~2 hrs/week across 4 sales reps manually deduplicating and correcting records | Salesforce deduplication complete. Duplicate rate under 5%. Forecast accuracy improves by next board cycle. | 25000 | XL — Extra Large | ⚪ 01 - Not Started | 0% |  | TBD | Feb | Escalated by CEO | FALSE | FALSE | 🔵 Capacity Unlock | 25% | 0 | 0
F-003 | 2025-01-22 | Dan Brooks | Technology | Evaluate and select a data warehouse solution | Analytics are pulled manually from 4 systems. No single source of truth for business performance data. | Tech Request | Financial Visibility | CTO | 13 - Game Changer | A data warehouse unlocks automated reporting across all business metrics. | 5 - Growing Pain | Manageable now but every new data source makes this worse. | 8 - Customer-Driven | CTO and CFO both behind this. Tied to board reporting improvement. | 8.8 | Analytics stays fragmented. Manual pulls continue burning time. Decision-making quality suffers. | ~6 hrs/week across finance and ops manually pulling and reconciling data. | Data warehouse selected and implemented. Key metrics auto-populate. Manual reporting eliminated. | 50000 | XL — Extra Large | 🔍 02 - Under Review | 10% | RFP sent to 3 vendors. Decision expected in 3 weeks. | Jonathon Pace | June |  | FALSE | FALSE | 🔴 Risk Mitigation | 25% | 0 | 0
F-004 | 2025-01-10 | Lisa Torres | Customer Success | Implement automated client health scoring | CSMs manually track 50+ accounts with no early warning system. Churn is discovered reactively, usually too late to save. | AI Initiative | Revenue Growth | VP Customer Success | 13 - Game Changer | Proactive churn prevention directly protects ARR. Every point of churn reduction has immediate revenue impact. | 13 - Time Bomb | We lost 2 accounts last month that showed warning signs 60 days earlier. This is actively costing us. | 8 - Customer-Driven | VP CS sponsors this. Serves 5 CSMs and protects revenue for the entire business. | 12 | We will continue losing accounts we could have saved. Estimated $200K ARR at risk in next 90 days based on current at-risk signals. | Each CSM manually reviews 10+ accounts weekly — approximately 3 hrs/week per CSM (15 hrs total). | Health score dashboard live. CSMs receive automated alerts 60 days before predicted churn. 30-day false positive rate under 20%. | 60000 | M — Medium | 🔴 05 - Off Track | 70% | Had to put down for establishing The Filter as core operating cadence. | Jonathon Pace | Dec |  | FALSE | FALSE | 🟢 Revenue Growth | 10% | 2 | 1
F-005 | 2025-01-11 | Tom Reid | Technology | API rate limit monitoring & alerting | Third-party API calls are hitting rate limits silently. Failures surface in customer complaints, not logs. | Tech Request | Risk Reduction | CTO | 8 - Major Lift | Silent failures = customer-facing errors we don't catch first. | 8 - Window Closing | Frequency of incidents increasing. Two client escalations last month. | 5 - Leadership Priority | CTO-driven. Impacts all product features using external APIs. | 7.4 | Continued silent failures erode client trust and increase churn risk. | ~2 hrs/week engineering triage on API failure tickets. | Zero undetected API rate limit failures. Alert fires before customer impact. | 12000 | S — Small | 🟢 03 - In Progress | 70% | Alert system 70% built. On track for month-end. | Nathan Harris | Feb |  | FALSE | FALSE | 🔵 Capacity Unlock | 5% | 3 | 1
F-006 | 2025-01-23 | Fiona Lee | HR | Define career leveling framework for all roles | No career levels exist. Compensation and promotion decisions are entirely discretionary. Causing equity concerns. | People & Culture | Talent Retention | CHRO | 8 - Major Lift | Career framework directly impacts retention, fairness, and hiring competitiveness. | 8 - Window Closing | Two high-performers flagged lack of career clarity as a flight risk in recent 1:1s. | 5 - Leadership Priority | CHRO and CEO aligned. Not yet a team-wide ask but risk is real. | 7.4 | Continued flight risk for high performers. Comp decisions stay inconsistent and legally exposed. | ~3 hrs/week CHRO on ad-hoc comp and promotion conversations without a framework. | Leveling framework defined for all roles. Every employee knows their level and the criteria for the next. | 22000 | L — Large | ⚪ 01 - Not Started | 0% |  | TBD | May |  | FALSE | FALSE | 🔵 Capacity Unlock | 15% | 0 | 0
F-007 | 2025-01-13 | Chris Alvarez | Sales | Build outbound sequence for mid-market segment | No structured outbound motion exists for the 100-500 employee segment. Reps are winging it. | Strategic Project | Revenue Growth | VP Sales | 13 - Game Changer | Mid-market is our highest-margin segment and has zero structured coverage. | 8 - Window Closing | Competitors are visibly increasing activity in this segment. | 8 - Customer-Driven | VP Sales and CEO aligned. Revenue team fully behind this. | 10 | Leave mid-market to competitors while we stay reactive on inbound only. | 0 structured outbound touches to 200+ qualified accounts sitting in CRM. | 5-touch outbound sequence live. 20+ meetings booked per month from mid-market. | 75000 | L — Large | 🟡 04 - At Risk | 20% | Sequence built but rep adoption lagging. Need enablement session. | Isaac James | Feb |  | TRUE | FALSE | 🔴 Risk Mitigation | 15% | 3 | 1
F-008 | 2025-01-14 | Amy Foster | HR | Redesign new hire onboarding for remote employees | Remote onboarding is a copy of in-person process. New hires report feeling disconnected after 90 days. | People & Culture | Talent Retention | CHRO | 5 - Solid Improvement | Meaningfully improves remote employee retention and ramp time. | 5 - Growing Pain | Hiring pace increasing. Each bad onboarding compounds retention risk. | 3 - Team Request | HR-led initiative. Limited external signal but internal pain is clear. | 4.6 | Continued early attrition among remote hires. Ramp time stays at 90+ days. | Avg 90-day ramp vs 60-day benchmark. 2 remote hire exits in past quarter. | Remote new hire NPS above 8. 60-day ramp achieved for 80% of hires. | 9000 | M — Medium | 🔵 06 - Delivered | 100% | New framework drafted. Piloting with next 2 hires. | TBD | Mar |  | FALSE | FALSE | 🟢 Revenue Growth | 10% | 0 | 0
F-009 | 2025-01-15 | Ben Walsh | Operations | Document and standardize client delivery process | Each delivery lead runs engagements differently. No standard playbook means inconsistent client experience. | Process Improvement | Operational Efficiency | COO | 8 - Major Lift | Standardization is a prerequisite for scale. Can't hire without it. | 8 - Window Closing | Hiring plan for Q2 requires this to exist first. Hard deadline. | 5 - Leadership Priority | COO-owned. CEO flagged this as a prerequisite for growth. | 7.4 | Can't scale delivery without a repeatable model. Hiring becomes a liability without it. | ~4 hrs/week per delivery lead re-inventing process. Inconsistent client outcomes. | Delivery playbook live. All engagements run from same framework. Onboarding new lead takes under 1 week. | 20000 | L — Large | 🔴 05 - Off Track | 40% | Behind on documentation. Resource pulled to client work. Needs reset. | Isaac James | Apr |  | TRUE | FALSE | 🔵 Capacity Unlock | 15% | 3 | 1
F-010 | 2025-01-12 | Dana Kim | Finance | Automate monthly close reporting package | Finance team spends 3 days each month manually assembling the close package from 5 different sources. | Process Improvement | Operational Efficiency | CFO | 8 - Major Lift | 3-day close package process is a material drag on finance capacity. | 5 - Growing Pain | Gets worse as headcount and entity count grows. Not urgent today but compounding. | 5 - Leadership Priority | CFO owns this. CEO relies on outputs for board reporting. | 6.2 | Finance continues losing 3 days per close cycle. Scales poorly as the business grows. | 36 person-days per year on manual assembly. | Monthly close package auto-generated in under 4 hours. Zero manual data pulls. | 18000 | M — Medium | 🔍 02 - Under Review | 10% | Evaluating automation tools. Decision needed by end of month. | Mark Mulligan | Mar |  | FALSE | FALSE | 🟡 Hard Cost Savings | 10% | 0 | 0
F-011 | 2025-01-17 | Rick Owens | Technology | Consolidate 3 internal Slack workspaces | Three separate Slack workspaces exist from acquisitions. Cross-team comms require switching between them. | Tech Request | Operational Efficiency | CTO | 3 - Incremental | Quality of life improvement. Business functions fine either way. | 1 - Whenever | No urgency at all. Entirely convenience-driven. | 3 - Team Request | Engineering and ops teams want this. No executive pressure. | 2.2 | Teams continue context-switching between workspaces. Manageable but annoying. | ~15 min/day per employee switching between workspaces. | Single unified Slack workspace. All historical channels migrated. | 3000 | S — Small | ⏸ 98 - Deferred | 0% | Low score. Deferred Q3. | TBD | Sep | Score doesn't support prioritizing now. | FALSE | FALSE | 🔵 Capacity Unlock | 5% | 0 | 0
F-012 | 2025-01-18 | Mel Torres | Marketing | Build content distribution calendar and workflow | Marketing creates content ad hoc with no editorial calendar. Publishing is inconsistent and reactive. | Process Improvement | Revenue Growth | CMO | 5 - Solid Improvement | Consistent content is a meaningful long-term revenue lever. | 5 - Growing Pain | Getting worse as content volume increases with no coordination system. | 5 - Leadership Priority | CMO-owned. CEO wants more brand presence in market. | 5 | Content stays inconsistent. Marketing team works reactively. Brand presence doesn't compound. | ~3 hrs/week per content creator on coordination overhead. | Editorial calendar live. Content published on consistent cadence. Zero missed publish windows. | 8000 | M — Medium | 🔵 06 - Delivered | 100% | Calendar built. Team trained. First scheduled month fully loaded. | Mark Mulligan | Feb |  | FALSE | FALSE | 🟢 Revenue Growth | 10% | 0 | 0
F-013 | 2025-01-19 | Sara Evans | Finance | Implement expense policy and approval workflow | Expense approvals happen over email with no policy document. Finance is manually reviewing every submission. | Process Improvement | Financial Visibility | CFO | 5 - Solid Improvement | Reduces finance manual review time and enforces consistent spend policy. | 8 - Window Closing | Board audit coming in Q2. No documented expense policy is a gap. | 5 - Leadership Priority | CFO-led. Board compliance pressure makes this a near-term requirement. | 6.2 | Q2 audit finds no documented expense policy. Finance continues manual review overhead. | ~5 hrs/week finance team on manual expense review and follow-up. | Policy documented. Approval workflow automated. Finance review time under 1 hr/week. | 10000 | S — Small | 🔍 02 - Under Review | 10% | Policy draft in review with CFO. Tool selection pending. | Lana Grace | Mar |  | FALSE | FALSE | 🔴 Risk Mitigation | 5% | 0 | 0
F-014 | 2025-01-20 | Jake Morris | Sales | Create competitive battle cards for top 3 competitors | Sales reps are losing deals to competitors they can't speak to. No battle cards exist. | Strategic Project | Revenue Growth | VP Sales | 8 - Major Lift | Directly impacts win rate in competitive situations. | 8 - Window Closing | Competitor activity increasing. Reps flagging this weekly. | 8 - Customer-Driven | VP Sales, CEO, and reps all flagging this. Strong multi-directional demand. | 8 | Continue losing competitive deals we should be winning. Win rate stays below benchmark. | ~1 hr/deal rep research time on competitive positioning. Inconsistent messaging. | Battle cards complete for top 3 competitors. Reps trained. Win rate in competitive deals improves 15%. | 35000 | S — Small | 🔵 06 - Delivered | 100% | Draft battle cards reviewed by VP Sales. Final edits this week. | Nathan Harris | Feb |  | FALSE | FALSE | 🟢 Revenue Growth | 5% | 0 | 0
F-015 | 2025-01-21 | Olivia Grant | Customer Success | Build onboarding checklist and milestone tracker | Client onboarding has no formal checklist. CSMs track status in personal notes. Milestones get missed. | Process Improvement | Operational Efficiency | VP Customer Success | 8 - Major Lift | Onboarding quality directly impacts time-to-value and early retention. | 5 - Growing Pain | Gets worse as client count increases. Manageable now, not at 2x. | 8 - Customer-Driven | VP CS owns. Clients have complained about unclear onboarding milestones. | 6.8 | Continue inconsistent onboarding. Time-to-value stays long. Early churn risk stays elevated. | ~2 hrs/client onboarding coordination overhead per CSM. | Onboarding checklist standardized. All milestones tracked in one place. Time-to-value under 30 days. | 14000 | M — Medium | 🟡 04 - At Risk | 30% | Tracker built but adoption uneven. Two CSMs not using it consistently. | Nathan Harris | Mar |  | FALSE | FALSE | 🟢 Revenue Growth | 10% | 2 | 1
F-016 | 2025-01-16 | Nina Patel | Product | User interview program — quarterly cadence | Product decisions are made from support tickets and gut feel. No structured customer input process. | Strategic Project | Revenue Growth | VP Product | 8 - Major Lift | Customer input directly improves roadmap quality and reduces wasted build cycles. | 3 - Backburner | No hard deadline. Pain is real but team is heads-down on current sprint. | 8 - Customer-Driven | VP Product and CEO both behind this. Customers have asked for more input opportunities. | 6 | Continue building features customers don't want. Wasted sprint cycles and roadmap misalignment. | Zero structured customer interviews in past 6 months. | Quarterly user interview program live. 8+ interviews per cycle. Insights fed into roadmap planning. | 15000 | S — Small | ⚪ 01 - Not Started | 0% |  | TBD | May |  | FALSE | FALSE | 🟢 Revenue Growth | 5% | 0 | 0
F-017 | 2025-01-30 | Iris Wong | HR | Launch employee pulse survey program | No employee sentiment data exists. Engagement issues surface only in exit interviews. | People & Culture | Talent Retention | CHRO | 5 - Solid Improvement | Early sentiment data allows proactive retention before people disengage. | 5 - Growing Pain | Headcount increasing. Engagement risk scales with it. | 3 - Team Request | HR-led. Employees have asked for more feedback channels. | 4.6 | Continue discovering engagement issues too late. Early attrition stays elevated. | Zero engagement signal between annual reviews. | Quarterly pulse survey live. Response rate above 70%. Action items tracked per cycle. | 7000 | S — Small | 🔍 02 - Under Review | 10% | Tool selection in progress. Two options being evaluated. | TBD | Apr |  | FALSE | FALSE | 🔴 Risk Mitigation | 5% | 0 | 0
F-018 | 2025-01-24 | Sam Carter | Operations | Implement weekly ops review cadence | No weekly operational review exists. Leadership has no shared visibility into what is and isn't moving. | Process Improvement | Operational Efficiency | COO | 13 - Game Changer | A functioning ops review is the foundation of every other operational improvement. | 13 - Time Bomb | Without this, everything else we build has no review mechanism. | 13 - External + Internal Pressure | COO, CEO, and board all flagging operational visibility as a concern. | 13 | No mechanism to catch problems before they compound. Everything stays reactive. | ~5 hrs/week leadership in reactive 1:1s that a structured review would replace. | Weekly ops review running for 60 days straight. Attendance 100%. Issues caught before escalating. | 0 | S — Small | 🟢 03 - In Progress | 40% | Week 3 of cadence. Strong attendance. Format still being refined. | Justin Bo | Feb |  | FALSE | FALSE | 🟡 Hard Cost Savings | 5% | 3 | 1
F-019 | 2025-01-25 | Raj Mehta | Product | Rebuild pricing page and packaging for self-serve | Current pricing page has 3 tiers with unclear differentiation. Conversion rate is below benchmark. | Strategic Project | Revenue Growth | VP Product | 13 - Game Changer | Pricing page is a direct revenue lever. Conversion improvement is compounding. | 8 - Window Closing | Competitor launched cleaner pricing last month. We're losing the comparison. | 8 - Customer-Driven | Sales and product leadership aligned. Prospect feedback is clear. | 10 | Continue losing self-serve conversions to clearer competitor positioning. | Sales team spending ~1 hr/deal explaining pricing that the page should handle. | New pricing page live. Self-serve conversion improves 20%. Sales time on pricing questions drops. | 90000 | M — Medium | 🔴 05 - Off Track | 90% | Design approved but engineering bandwidth missing. Escalated to CTO. | Nathan Harris | Mar |  | TRUE | FALSE | 🟢 Revenue Growth | 10% | 2 | 1
F-020 | 2025-01-26 | Kate Burns | Marketing | Launch partner referral program | No formal referral mechanism exists despite strong NPS. Word of mouth is happening but untracked. | Strategic Project | Revenue Growth | CMO | 8 - Major Lift | Referral program directly adds qualified pipeline with low acquisition cost. | 3 - Backburner | No urgency. Opportunity cost but no hard deadline. | 5 - Leadership Priority | CMO-owned. CEO supportive but not pushing. | 5.4 | Leave referral revenue on the table while word of mouth happens untracked. | Zero structured referral touches to customers with NPS above 9. | Referral program live. 10+ referrals per quarter tracked. CAC from referrals 60% below paid. | 45000 | L — Large | ⏸ 98 - Deferred | 0% | Good idea. Bandwidth not available until Q3. | TBD | Aug | Deferred pending Q2 capacity review. | FALSE | FALSE | 🔵 Capacity Unlock | 15% | 0 | 0
F-021 | 2025-01-27 | Ethan Cross | Technology | Set up staging environment parity with production | Staging environment is 2 versions behind production. Bugs are missed and appear in prod unexpectedly. | Tech Request | Risk Reduction | CTO | 8 - Major Lift | Staging parity prevents production incidents. Direct quality and trust impact. | 8 - Window Closing | Three production incidents in past 6 weeks traced back to staging gap. | 5 - Leadership Priority | CTO owns. Recent incidents have CEO attention. | 7.4 | Production incidents continue. Customer trust erodes. Engineering credibility suffers. | ~4 hrs/incident response time. 3 incidents in 6 weeks. | Staging matches production. Zero production-only incidents for 60 days. | 16000 | M — Medium | 🟡 04 - At Risk | 30% | Infrastructure work started. Timeline slipping due to legacy config complexity. | Nathan Harris | Feb |  | FALSE | FALSE | 🟢 Revenue Growth | 10% | 2 | 1
F-022 | 2025-01-09 | James Park | Engineering | Migrate dev environment to containerized setup | New engineer onboarding takes 2 full days of setup. Inconsistent environments causing 'works on my machine' bugs in staging. | Tech Request | Operational Efficiency | CTO | 5 - Solid Improvement | Improves developer experience and onboarding speed. Real but not business-critical. | 3 - Backburner | No immediate deadline. We hire engineers infrequently. Pain is real but manageable for now. | 3 - Team Request | Primarily benefits the 6-person engineering team. Low visibility outside that group. | 3.8 | Onboarding stays slow. Environment bugs continue burning engineering hours. Manageable but annoying. | 2 days lost per new hire onboarding. ~1 hr/week per engineer on environment issues. | New engineer fully set up in under 2 hours. Zero environment-related staging bugs for 30 days. | 8000 | S — Small | ⚪ 01 - Not Started | 0% |  | TBD | Apr | Good idea, not this quarter. Revisit Q3. | FALSE | FALSE | 🔴 Risk Mitigation | 5% | 0 | 0
F-023 | 2025-01-29 | Paul Grant | Finance | Build department-level budget vs actuals reporting | Department heads have no visibility into budget vs actuals. Finance is fielding daily questions. | Process Improvement | Financial Visibility | CFO | 8 - Major Lift | Budget visibility empowers department heads and reduces finance overhead. | 8 - Window Closing | Q2 budget cycle starts in 6 weeks. This needs to exist before then. | 8 - Customer-Driven | CFO, department heads, and CEO all asking for this. | 8 | Department heads continue flying blind. Finance spends 5+ hrs/week on manual reporting requests. | ~5 hrs/week finance team responding to manual budget inquiries. | Every department head has live budget vs actuals view. Finance inquiry volume drops 80%. | 19000 | M — Medium | 🟢 03 - In Progress | 80% | Report built for 4 of 6 departments. Two remaining this week. | Tyra Barden | Mar |  | FALSE | FALSE | 🟡 Hard Cost Savings | 10% | 2 | 1
F-024 | 2025-01-28 | Zoe Hall | Customer Success | Build QBR template and delivery process | QBRs are inconsistent across CSMs. Some clients get polished decks, others get ad hoc calls. | Process Improvement | Operational Efficiency | VP Customer Success | 5 - Solid Improvement | Consistent QBRs improve retention and expansion revenue signal. | 3 - Backburner | Not urgent. But inconsistency is visibly affecting enterprise client relationships. | 3 - Team Request | CSM team is asking for this. VP CS supportive but not driving urgently. | 3.8 | Enterprise clients continue getting inconsistent treatment. Expansion signals missed. | ~3 hrs/QBR prep per CSM with no template. | QBR template standardized. All enterprise accounts on consistent cadence. Expansion revenue tracked. | 11000 | S — Small | ⚪ 01 - Not Started | 0% |  | TBD | Apr |  | FALSE | FALSE | 🔵 Capacity Unlock | 5% | 0 | 0
F-025 | 2025-01-31 | Leo Crane | Operations | Build vendor scorecard and quarterly review process | 15 active vendors with no performance tracking. Underperforming vendors stay on contract. | Process Improvement | Risk Reduction | COO | 5 - Solid Improvement | Vendor accountability reduces risk and surfaces renegotiation opportunities. | 3 - Backburner | No urgency but vendor costs growing. Value being left on table. | 3 - Team Request | COO-initiated. Finance supportive for cost savings angle. | 3.8 | Underperforming vendors stay on. Cost optimization opportunities missed. | ~2 hrs/month per vendor manager on informal check-ins with no documented outcomes. | Vendor scorecard live. Quarterly reviews scheduled. One vendor renegotiated or replaced per quarter. | 12000 | S — Small | ⏸ 98 - Deferred | 0% | Good idea. Not enough bandwidth this quarter. | TBD | July | Deferred to Q3. | FALSE | FALSE | 🔵 Capacity Unlock | 5% | 0 | 0
F-026 | 2025-02-01 | Mia Ross | Product | Define and instrument product usage analytics | No product analytics beyond login counts. Feature adoption is unknown. Roadmap prioritization is guesswork. | Tech Request | Revenue Growth | VP Product | 13 - Game Changer | Usage data is the foundation of every product decision. Missing it costs compoundingly. | 8 - Window Closing | Roadmap planning for H2 starts in 6 weeks. Need data before that. | 8 - Customer-Driven | VP Product and CEO both urgent on this. Investors have asked about retention metrics. | 10 | Continue building features without knowing if they're used. Roadmap stays assumption-driven. | Zero feature adoption data. Product team relying on support tickets and anecdote. | Key feature events instrumented. Weekly usage report live. Roadmap backed by adoption data. | 30000 | L — Large | 🟢 03 - In Progress | 70% | Instrumentation 60% complete. Dashboard being built in parallel. | Nathan Harris | Apr |  | FALSE | FALSE | 🟢 Revenue Growth | 15% | 3 | 1
F-027 | 2025-02-02 | Aaron Dale | Sales | Implement deal review process for $50K+ opportunities | Large deals close at the same rate as small ones. No structured review for high-value opportunities. | Process Improvement | Revenue Growth | VP Sales | 8 - Major Lift | Even a 10% improvement in large deal close rate has material revenue impact. | 5 - Growing Pain | Large deal pipeline growing. No review process means no leverage point. | 5 - Leadership Priority | VP Sales-led. CEO has flagged large deal performance. | 6.2 | Large deals continue closing at sub-optimal rates. No feedback loop to improve. | ~2 large deals/month closed without structured review. | Deal review cadence for $50K+ opps running weekly. Large deal close rate improves 10%. | 55000 | S — Small | 🔴 05 - Off Track | 10% | Process designed but VP Sales not running it consistently. Needs accountability reset. | Nathan Harris | Mar |  | FALSE | FALSE | 🔴 Risk Mitigation | 5% | 3 | 1
F-028 | 2025-02-03 | Claire West | Marketing | Build SEO content program targeting ICP keywords | Zero organic search presence. All pipeline is paid or referral. No compounding traffic channel. | Strategic Project | Revenue Growth | CMO | 8 - Major Lift | SEO is a compounding channel. 6-month investment creates years of pipeline. | 5 - Growing Pain | CAC increasing on paid. Organic is the offset. Later we start, longer the ramp. | 5 - Leadership Priority | CMO and CEO aligned on reducing paid dependence. | 6.2 | Continue 100% reliance on paid acquisition. CAC stays high. No compounding traffic channel. | Zero organic content published targeting ICP keywords. | 12 pillar pieces live. Ranking for 10+ ICP keywords. Organic contributing 15%+ of pipeline. | 28000 | L — Large | 🟡 04 - At Risk | 20% | Keyword research done. Writer not secured. Timeline at risk. | TBD | May |  | FALSE | FALSE | 🟢 Revenue Growth | 15% | 3 | 1
F-029 | 2025-02-04 | Derek Shaw | Operations | Create master project intake and triage process | Projects arrive via Slack, email, and hallway conversations. No single intake point. Work starts before it is evaluated. | Process Improvement | Operational Efficiency | COO | 13 - Game Changer | This IS The Filter. Without intake, the scoring system has no front door. | 13 - Time Bomb | Every day without intake, un-scored work is starting. The system leaks. | 13 - External + Internal Pressure | COO, CEO, and every department head flagging the same chaos. | 13 | Unsanctioned work continues starting. Capacity is consumed by things that never made the list. | Estimated 20% of active work in flight was never formally submitted or scored. | Every new work request enters through single intake form. Zero un-scored work in active delivery. | 0 | S — Small | 🟢 03 - In Progress | 20% | Intake form live. Training done. Adoption tracking started. | Alex Ross | Feb |  | TRUE | TRUE | 🔵 Capacity Unlock | 5% | 3 | 1
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0
[31 empty] | 0 | 0

## 📊 Exec Dashboard
THE FILTER — EXECUTIVE DASHBOARD
PORTFOLIO SUMMARY - Count of Total Requests by Status
| TOTAL | IN PROGRESS | AT RISK | OFF TRACK | UNDER REVIEW | DEFERRED | DELIVERED | NOT STARTED | ⚡ FLAGGED
| 30 | 5 | 4 | 4 | 4 | 3 | 4 | 6 | 4
PORTFOLIO ANALYTICS
Details for Status Reporting
⚡ FAST TRACK & ESCALATED
🔴 OFF TRACK
Title | Description | Impact | Urgency | Audience | Score | Lead | Status | Latest Update | Target | % Complete
Document and standardize client delivery process | Each delivery lead runs engagements differently. No standard playbook means inconsistent client experience. | 8 - Major Lift | 8 - Window Closing | 5 - Leadership Priority | 7.4 | Isaac James | 🔴 05 - Off Track | Behind on documentation. Resource pulled to client work. Needs reset. | Apr | 40%
Rebuild pricing page and packaging for self-serve | Current pricing page has 3 tiers with unclear differentiation. Conversion rate is below benchmark. | 13 - Game Changer | 8 - Window Closing | 8 - Customer-Driven | 10 | Nathan Harris | 🔴 05 - Off Track | Design approved but engineering bandwidth missing. Escalated to CTO. | Mar | 90%
🟡 AT RISK
Title | Description | Impact | Urgency | Audience | Score | Lead | Status | Latest Update | Target | % Complete
Build outbound sequence for mid-market segment | No structured outbound motion exists for the 100-500 employee segment. Reps are winging it. | 13 - Game Changer | 8 - Window Closing | 8 - Customer-Driven | 10 | Isaac James | 🟡 04 - At Risk | Sequence built but rep adoption lagging. Need enablement session. | Feb | 20%
🟢 IN PROGRESS
Title | Description | Impact | Urgency | Audience | Score | Lead | Status | Latest Update | Target | % Complete
Create master project intake and triage process | Projects arrive via Slack, email, and hallway conversations. No single intake point. Work starts before it is evaluated. | 13 - Game Changer | 13 - Time Bomb | 13 - External + Internal Pressure | 13 | Alex Ross | 🟢 03 - In Progress | Intake form live. Training done. Adoption tracking started. | Feb | 20%
📋 ACTIVE PROJECTS
🔴 OFF TRACK
Title | Description | Impact | Urgency | Audience | Score | Lead | Status | Latest Update | Target | % Complete
Implement automated client health scoring | CSMs manually track 50+ accounts with no early warning system. Churn is discovered reactively, usually too late to save. | 13 - Game Changer | 13 - Time Bomb | 8 - Customer-Driven | 12 | Jonathon Pace | 🔴 05 - Off Track | Had to put down for establishing The Filter as core operating cadence. | Dec | 70%
Implement deal review process for $50K+ opportunities | Large deals close at the same rate as small ones. No structured review for high-value opportunities. | 8 - Major Lift | 5 - Growing Pain | 5 - Leadership Priority | 6.2 | Nathan Harris | 🔴 05 - Off Track | Process designed but VP Sales not running it consistently. Needs accountability reset. | Mar | 10%
🟡 AT RISK
Title | Description | Impact | Urgency | Audience | Score | Lead | Status | Latest Update | Target | % Complete
Build onboarding checklist and milestone tracker | Client onboarding has no formal checklist. CSMs track status in personal notes. Milestones get missed. | 8 - Major Lift | 5 - Growing Pain | 8 - Customer-Driven | 6.8 | Nathan Harris | 🟡 04 - At Risk | Tracker built but adoption uneven. Two CSMs not using it consistently. | Mar | 30%
Set up staging environment parity with production | Staging environment is 2 versions behind production. Bugs are missed and appear in prod unexpectedly. | 8 - Major Lift | 8 - Window Closing | 5 - Leadership Priority | 7.4 | Nathan Harris | 🟡 04 - At Risk | Infrastructure work started. Timeline slipping due to legacy config complexity. | Feb | 30%
Build SEO content program targeting ICP keywords | Zero organic search presence. All pipeline is paid or referral. No compounding traffic channel. | 8 - Major Lift | 5 - Growing Pain | 5 - Leadership Priority | 6.2 | TBD | 🟡 04 - At Risk | Keyword research done. Writer not secured. Timeline at risk. | May | 20%
🟢 IN PROGRESS
Title | Description | Impact | Urgency | Audience | Score | Lead | Status | Latest Update | Target | % Complete
API rate limit monitoring & alerting | Third-party API calls are hitting rate limits silently. Failures surface in customer complaints, not logs. | 8 - Major Lift | 8 - Window Closing | 5 - Leadership Priority | 7.4 | Nathan Harris | 🟢 03 - In Progress | Alert system 70% built. On track for month-end. | Feb | 70%
Implement weekly ops review cadence | No weekly operational review exists. Leadership has no shared visibility into what is and isn't moving. | 13 - Game Changer | 13 - Time Bomb | 13 - External + Internal Pressure | 13 | Justin Bo | 🟢 03 - In Progress | Week 3 of cadence. Strong attendance. Format still being refined. | Feb | 40%
Build department-level budget vs actuals reporting | Department heads have no visibility into budget vs actuals. Finance is fielding daily questions. | 8 - Major Lift | 8 - Window Closing | 8 - Customer-Driven | 8 | Tyra Barden | 🟢 03 - In Progress | Report built for 4 of 6 departments. Two remaining this week. | Mar | 80%
Define and instrument product usage analytics | No product analytics beyond login counts. Feature adoption is unknown. Roadmap prioritization is guesswork. | 13 - Game Changer | 8 - Window Closing | 8 - Customer-Driven | 10 | Nathan Harris | 🟢 03 - In Progress | Instrumentation 60% complete. Dashboard being built in parallel. | Apr | 70%
🔍 UNDER REVIEW — Analysis in progress
🔍 UNDER REVIEW
Title | Description | Impact | Urgency | Audience | Score | Lead | Status | Latest Update | Target | % Complete
Evaluate and select a data warehouse solution | Analytics are pulled manually from 4 systems. No single source of truth for business performance data. | 13 - Game Changer | 5 - Growing Pain | 8 - Customer-Driven | 8.8 | Jonathon Pace | 🔍 02 - Under Review | RFP sent to 3 vendors. Decision expected in 3 weeks. | June | 10%
Automate monthly close reporting package | Finance team spends 3 days each month manually assembling the close package from 5 different sources. | 8 - Major Lift | 5 - Growing Pain | 5 - Leadership Priority | 6.2 | Mark Mulligan | 🔍 02 - Under Review | Evaluating automation tools. Decision needed by end of month. | Mar | 10%
Implement expense policy and approval workflow | Expense approvals happen over email with no policy document. Finance is manually reviewing every submission. | 5 - Solid Improvement | 8 - Window Closing | 5 - Leadership Priority | 6.2 | Lana Grace | 🔍 02 - Under Review | Policy draft in review with CFO. Tool selection pending. | Mar | 10%
Launch employee pulse survey program | No employee sentiment data exists. Engagement issues surface only in exit interviews. | 5 - Solid Improvement | 5 - Growing Pain | 3 - Team Request | 4.6 | TBD | 🔍 02 - Under Review | Tool selection in progress. Two options being evaluated. | Apr | 10%
⏸ DEFERRED — Parked for future review
⏸ DEFERRED
Title | Description | Impact | Urgency | Audience | Score | Lead | Status | Latest Update | Target | % Complete
Consolidate 3 internal Slack workspaces | Three separate Slack workspaces exist from acquisitions. Cross-team comms require switching between them. | 3 - Incremental | 1 - Whenever | 3 - Team Request | 2.2 | TBD | ⏸ 98 - Deferred | Low score. Deferred Q3. | Sep | 0%
Launch partner referral program | No formal referral mechanism exists despite strong NPS. Word of mouth is happening but untracked. | 8 - Major Lift | 3 - Backburner | 5 - Leadership Priority | 5.4 | TBD | ⏸ 98 - Deferred | Good idea. Bandwidth not available until Q3. | Aug | 0%
Build vendor scorecard and quarterly review process | 15 active vendors with no performance tracking. Underperforming vendors stay on contract. | 5 - Solid Improvement | 3 - Backburner | 3 - Team Request | 3.8 | TBD | ⏸ 98 - Deferred | Good idea. Not enough bandwidth this quarter. | July | 0%
⚪ NOT STARTED — Not yet picked up
⚪ NOT STARTED
Title | Description | Impact | Urgency | Audience | Score | Lead | Status | Latest Update | Target | % Complete
Build rolling 13-week cash flow model | Finance has no forward visibility on cash position. CFO is manually updating a static spreadsheet weekly with no scenario modeling. | 13 - Game Changer | 8 - Window Closing | 8 - Customer-Driven | 10 | TBD | ⚪ 01 - Not Started |  | Sep | 0%
CRM data cleanup and deduplication | Salesforce has 40% duplicate contact records from 3 years of manual entry. Causing missed follow-ups and inaccurate forecasting. | 5 - Solid Improvement | 13 - Time Bomb | 8 - Customer-Driven | 8.8 | TBD | ⚪ 01 - Not Started |  | Feb | 0%
Define career leveling framework for all roles | No career levels exist. Compensation and promotion decisions are entirely discretionary. Causing equity concerns. | 8 - Major Lift | 8 - Window Closing | 5 - Leadership Priority | 7.4 | TBD | ⚪ 01 - Not Started |  | May | 0%
User interview program — quarterly cadence | Product decisions are made from support tickets and gut feel. No structured customer input process. | 8 - Major Lift | 3 - Backburner | 8 - Customer-Driven | 6 | TBD | ⚪ 01 - Not Started |  | May | 0%
Migrate dev environment to containerized setup | New engineer onboarding takes 2 full days of setup. Inconsistent environments causing 'works on my machine' bugs in staging. | 5 - Solid Improvement | 3 - Backburner | 3 - Team Request | 3.8 | TBD | ⚪ 01 - Not Started |  | Apr | 0%
Build QBR template and delivery process | QBRs are inconsistent across CSMs. Some clients get polished decks, others get ad hoc calls. | 5 - Solid Improvement | 3 - Backburner | 3 - Team Request | 3.8 | TBD | ⚪ 01 - Not Started |  | Apr | 0%

## ⚖ Capacity Check
CAPACITY CHECK
A sanity check, not a staffing model. Each active initiative carries a rough load weight based on its effort size. We sum each team's active load and flag anyone carrying more than they can sustainably absorb. The system surfaces the overload — the humans decide what to pause before adding more.
HOW LOAD WEIGHT WORKS
Effort size → load weight: S = 1 M = 2 L = 3 XL = 5 · Soft ceiling per team = 6
Only active work counts — In Progress, At Risk, Off Track. Delivered, deferred, and not-started items don't consume capacity.
Team | Active Items | Load Weight | Capacity | % of Ceiling | Signal
Customer Success | 2 | 4 | 6 | 66.67% | HEALTHY
Finance | 1 | 2 | 6 | 33.33% | HEALTHY
Marketing | 1 | 3 | 6 | 50% | HEALTHY
Operations | 3 | 9 | 6 | 150% | OVERLOADED
Product | 2 | 5 | 6 | 83.33% | AT CAPACITY
Sales | 2 | 6 | 6 | 100% | AT CAPACITY
Technology | 2 | 5 | 6 | 83.33% | AT CAPACITY
All Teams | 13 | 34 | 42 | 80.95%
This is the conversation a capacity check forces: before activating anything new, we look at which team would own it and whether they're already over the line. An overloaded team is usually why good work goes off-track — not because the work was wrong, but because there was too much of it at once.
Adjust each team's soft ceiling in column E to match real bandwidth. Weights and signals recalculate automatically from the live list.

## 👤 Resource Capacity
RESOURCE CAPACITY
A manager-maintained view of who is actually carrying what. Each person’s time splits into BAU (keeping the business running) and capacity available for initiatives. The system sums each person’s ACTIVE initiative allocations and flags anyone committed past their available capacity. The lightest possible timecard — no employee input, the manager just keeps it honest.
HOW THIS WORKS
BAU % = run-the-business time (the input you set). Available % = 100% − BAU. Committed % = the sum of this person’s active initiative allocations, pulled from the “% Allocated” column on Raw Data. Committed past Available = OVERLOADED.
Over capacity: | 1 of 6 people |  | Unassigned active load: |  | 15% (no named owner)
Name | Team | BAU % | Available for Initiatives | Committed (Active Work) | Remaining | Signal
Nathan Harris | Technology | 50% | 50% | 55% | -5% | OVERLOADED
Isaac James | Sales | 65% | 35% | 30% | 5% | AT CAPACITY
Jonathon Pace | Technology | 70% | 30% | 10% | 20% | HEALTHY
Tyra Barden | Finance | 70% | 30% | 10% | 20% | HEALTHY
Justin Bo | Operations | 75% | 25% | 5% | 20% | HEALTHY
Alex Ross | Operations | 75% | 25% | 5% | 20% | HEALTHY
Maintenance: update BAU % when a role changes, and % Allocated on Raw Data when work is assigned. Only In Progress / At Risk / Off Track items count toward load. TBD = active work with no owner — assign it or it stays nobody’s job.

## 📐 ROI Calculator
THE FILTER — LINE ITEM ROM ESTIMATOR
A starting point for analysis during Under Review. Pick the primary driver, fill 2–3 inputs, get a rough-order-of-magnitude (ROM) number.
STEP 1 — SELECT THE VALUE DRIVER
Primary Value Driver | 🟢 Revenue Growth
STEP 2 — FILL IN THE INPUTS FOR YOUR DRIVER
🟢 REVENUE GROWTH
Expected new ARR or revenue unlocked ($) | 1000000 | Annual revenue this makes possible once done
Confidence level (%) | 50% | 100% = certain. 50% = real guess. Be honest.
500000
🔵 CAPACITY UNLOCK
# of people losing time to this | 3 | Full-time equivalents affected
Hours per week wasted per person | 4 | Recurring. Be honest.
Avg loaded hourly rate ($) | 85 | ~$75–100 typical. Higher for leaders.
0
🟡 HARD COST SAVINGS
Annual vendor / tool / contract spend ($) | 25000 | What you're paying right now that this eliminates
Annual headcount cost eliminated ($) | 75000 | Loaded salary of role(s) removed or avoided
Other recurring spend eliminated ($) | 0 | Licenses, services, overhead
0
🔴 RISK MITIGATION
Cost of the bad outcome ($) | 300000 | Fine, churn event, breach, outage — realistic worst case
Likelihood of occurance without this project | High (75%)
75%
0
500000
STEP 3 — YOUR ROM NUMBER
💰 Annual opportunity cost of not acting | 500000
Meaningful cost of inaction. Worth serious consideration.
ROM = Rough Order of Magnitude. Fill in the section that matches your driver — leave the others alone. This is a starting point for the Under Review conversation, not a financial model. Use it to get directional on whether the cost of inaction is real.

## 📊 Chart Data (hidden)
Effort | In Progress | At Risk | Off Track | Under Review | Deferred | Not Started | Department | In Progress | At Risk | Off Track | Under Review | Deferred | Not Started | Value Driver | In Progress | At Risk | Off Track | Under Review | Deferred | Not Started
Small | 3 | 0 | 1 | 2 | 2 | 3 | Operations | 2 | 0 | 1 | 0 | 1 | 0 | Revenue Growth | 1 | 3 | 2 | 0 | 0 | 1
Medium | 1 | 2 | 2 | 1 | 0 | 0 | Finance | 1 | 0 | 0 | 2 | 0 | 1 | Capacity Unlock | 2 | 0 | 1 | 0 | 3 | 3
Large | 1 | 2 | 1 | 0 | 1 | 2 | Technology | 1 | 1 | 0 | 1 | 1 | 0 | Hard Cost Savings | 2 | 0 | 0 | 1 | 0 | 1
XL | 0 | 0 | 0 | 1 | 0 | 1 | Sales | 0 | 1 | 1 | 0 | 0 | 1 | Risk Mitigation | 0 | 1 | 1 | 3 | 0 | 1
[7 empty] | Marketing | 0 | 1 | 0 | 0 | 1 | 0
[7 empty] | HR | 0 | 0 | 0 | 1 | 0 | 1
[7 empty] | Product | 1 | 0 | 1 | 0 | 0 | 1
[7 empty] | Customer Success | 0 | 1 | 1 | 0 | 0 | 1
[7 empty] | Engineering | 0 | 0 | 0 | 0 | 0 | 1